## type1
|  | TopDown - UCP (Gustav Kerner in 1993) |  |  |  | $ | junior cost/hour | 12 |  | 5
[6 empty] | $ | senior cost/hour | 15 |  | =vnd
[6 empty] | $ | expert cost/hour | 18 |  | 21000
# | ## | items | TAP | TUP | TCF | EF | expected hour | actual hour | COST
|  | Total | 2 | 10 | 1.32 | 2.89 | 105.25 | 0 | 1313 | 27573000
1 | 1 | login | 1 | 5 | 0.66 | 1.445 | 52.625 |  | 631.5
| 2 | logout | 1 | 5 | 0.66 | 1.445 | 52.625 |  | 631.5
0
0
0
0
0
0
0
|  | Risk | [6 empty] | 0
50
0
0
0
0

## type2
|  | Experienced (1996) |  | $ | junior cost/hour | 12
|  |  |  | $ | senior cost/hour | 15 |  | =vnd
|  |  |  | $ | expert cost/hour | 18 |  | 21000
# | ## | items | RUP cases | hour/case | expected hour | actual hour | COST
|  | Total |  |  | 73.4 | 0 | 880.8 | 18496800
1 |  | FUNCTION |  |  |  |  | 0
|  | login (analyze, testcase writing, executing, log bug, test report) | 8 | 0.2 | 1.6 |  | 19.2
|  | logout (analyze, testcase writing, executing, log bug, test report) | 8 | 0.2 | 1.6 |  | 19.2
0
0
0
0
0
0
0
|  | Risk |  |  |  |  | 0
0
0
0
0
0
2 |  | NON-FUNCTION |  |  |  |  | 0
|  | login (analyze, testcase writing, executing, log bug, test report) | 8 | 0.2 | 1.6 |  | 19.2
|  | logout (analyze, testcase writing, executing, log bug, test report) | 8 | 0.2 | 1.6 |  | 19.2
|  | Risk |  |  |  |  | 0
0
0
3 |  | BACK OFFICE |  |  |  |  | 0
|  | translation |  |  | 40 |  | 480
|  | offshore travelling |  |  | 10 |  | 120
|  | onsite travelling |  |  | 5 |  | 60
|  | administration |  |  | 10 |  | 120
|  | new employment |  |  | 2 |  | 24
Risk